## Risk Assessment
Risk Reference | Risk (Cause of risks to be entered in italics) |  |  | Current Level of Risk |  |  |  |  | Residual Level of Risk |  |  |  | Risk Owner (Responsible Areas are in italics) | Time Line for Completion of Additional Risk Treatments
|  | Consequences | Current Risk Treatments | Likelihood | Consequence | Risk Level | Ranking | Additional Risk Treatments | Likelihood | Consequence | Risk Level | Ranking
SUP_01 | Supervisor is not contactable/unavailable for an extended period of time | Advice and guidance cannot be given, possibly allowing misinformation and a lack of help when needed. | The unit co-ordinator can be approached for general information. | 1 | 2 | 2 | L | None Required | 1 | 2 | 2 | L | Engineering Department | N/A
PER_01 | Sickness or unrelated injury | Reduced work progress or complete stoppage. Can set behind the whole project causing stress. | Computers available at residence has required software to work on much of the project, allowing work to continue, abet at a slower pace. | 2 | 2 | 4 | L | None Required | 2 | 2 | 4 | L | Myself | N/A
PER_02 | Project work causes too much stress | Reduced ability to work on both project and other units. Can fall behind further increasing stress. | Maintain health level of commitment to work, while allowing for time spend outside of project and unit work. | 2 | 2 | 4 | L | None Required | 2 | 2 | 4 | L | Myself | N/A
ERG_01 | Bad posture or sitting position | Sore back, shoulders and neck. Will reduce productivity and act as a distraction preventing focused work. | Adjustable chairs with movable seat angle and back position allowing an ergonomic seating position. | 2 | 2 | 4 | L | None Required | 2 | 2 | 4 | L | Myself | N/A
ERG_02 | Repetitive Strain Injuries in hands or wrists | Computer work becomes painful impacting on both project work and unit work. | Regular breaks from computer work. | 2 | 2 | 4 | L | Implement regular wrist exercises. Use correct hand position according to ergonomic standards. | 1 | 2 | 2 | L | Myself | To be applied immediately
ERG_03 | Eye strain/soreness | Work must be stopped to rest eyes. | Correct ergonomic eye level and distance from screen. | 3 | 2 | 6 | M | Have regular breaks from computer work. | 2 | 2 | 4 | L | Myself | To be applied immediately
EQU_01 | Baxter robot breaks completely | Baxter cannot be used to test or demonstrate project. | Simulation software Gazebo can be used in place of Baxter for proof of concept. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Myself and Engineering Department | N/A
EQU_02 | Collision of Baxter robot with person | Affected area can have slight soreness. | Baxter's limited force application (lifting limit of 2kg) and slow motion ensures all collisions are low impact. | 2 | 1 | 2 | L | Area near Baxter to be clear of persons before and during use. | 1 | 1 | 1 | L | Myself | To be applied before testing with Baxter occurs
EQU_03 | Some systems of Baxter stop working | All the main functions are needed, and as such this could completely eliminate using Baxter. | Use of Gazebo simulation software in place of Baxter may be required but will be sufficient to perform tests and present the project. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Myself and Engineering Department | N/A
CMP_01 | Loss of data | Time and effort wasted by losing data due to hard drive crashes or data corruption. | Copies of all project files are on different computers and backed up on USB's | 2 | 3 | 6 | M | Use of cloud storage to add another backup of project data and allow syncing between devices. | 1 | 1 | 1 | L | Myself | To be applied immediately
CMP_02 | Workstation computer that connects to Baxter fails | Communication through workstation to Baxter and thus testing cannot be done. | Laptop is set up with required software and can be used instead of lab computer. Software can be reinstalled on a different computer in the lab. This would require a couple hours of work. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Engineering Department | N/A
CMP_03 | Either personal computer used for programming work fails | Limit personal computer work and therefore set back or slow down project work. | Multiple computers set up to work on. | 1 | 2 | 2 | L | None Required | 1 | 2 | 2 | L | Myself | N/A
SFT_01 | Communication software becomes unsupported | Cannot communicate and thus use the Baxter robot. | Gazebo Simulation Software can be used in place of Baxter robot. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Engineering Department | N/A
SFT_02 | MoveIT software becomes unsupported | Motion planning cannot be done using the software. Can cause a large setback. | Motion planning will require test with the Baxter robot, or use of Gazebo simulation software. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Engineering Department | N/A
SFT_03 | Rviz software becomes unsupported | Detailed information about Baxter cannot be displayed while testing. | Although less information can be obtained, tests can still be performed. Debugging of Baxter can be done by rqt_console software. | 1 | 2 | 2 | L | None Required | 1 | 2 | 2 | L | Engineering Department | N/A
SFT_04 | Visual Studios IED becomes unsupported | Programming cannot be done using Visual Studios, stopping relevant work. | Another IDE can be used in place to allow programming work to recommence. | 1 | 2 | 2 | L | None Required | 1 | 2 | 2 | L | Engineering Department | N/A
SFT_05 | Gazebo Simulation software becomes unsupported | Accurate simulation of Baxter robot in an environment cannot be done. Can slow down project development. | Physical testing with Baxter must replace simulation tests. | 1 | 3 | 3 | L | None Required | 1 | 3 | 3 | L | Engineering Department | N/A
|  |  |  | Activity Risk Rating |  |  |  |  | 1 |  |  |  | Low
SUP | Supervisor
PER | Personal
ERG | Ergonomics
EQU | Equipment
CMP | Computer
SFT | Software

## Risk Matrix
|  | Injuries | No injuries | First aid treatment | Medical treatment | Death or extensive injuries | Multiple deaths or severe permanent disabilities
|  | Financial Loss | <$50K or 5% of operational budget | <$50K-$250K or 10% of operational budget | <$250K-$3M or 25% of operational budget | <$3M-$10M or 50% of operational budget | >$10M or >50% of operational budget
|  | Asset Loss | Little or no impact on assets | Minor loss or damage to assets | Major damage to assets | Significant loss of assets | Complete loss of assets
|  | Interruption to Services | < 0.5 day | 0.5 day to 1 day | 1 day to <1 week | 1 week to 1 month | >1 month
|  | Reputation and Image | Unsubstantiated, low impact, low profile or no news items | Substantiated, low impact, low profile or low news items | Substantiated, public embarrassment, moderate impact, moderate news profile | Substantiated, public embarrassment, high impact, high news profile, third party actions | Substantiated, public embarrassment, very high multiple impacts, high widespread news profile, third party actions
|  | Consequences | Minor | Disruptive | Serious | Critical | Catastrophic
Description | Likelihood | Score | 1 | 2 | 3 | 4 | 5
Theoretically possible but not expected to occur during the life cycle of the activity or the lifetime of the equipment | Rare (<5% probability) | 1 | 1 (Low) | 2 (Low) | 3 (Low) | 4 (Low) | 5 (Moderate)
Possible that it may occur once during the life cycle of the activity or the lifetime of the equipment | Possible (5-10% probability) | 2 | 2 (Low) | 4 (Low) | 6 (Moderate) | 8 (Moderate) | 10 (Substantial)
This event may occur slightly more than twice during the life cycle of the activity or during the lifetime of the equipment | Occasional (10-25% probability) | 3 | 3 (Low) | 6 (Moderate) | 9 (Moderate) | 12 (Substantial) | 15 (High)
This event may occur frequently during the life cycle of the activity or during the lifetime of the equipment | Likely (25-50% probability) | 4 | 4 (Low) | 8 (Moderate) | 12 (Substantial) | 16 (High) | 20 (Extreme)
Expected to occur routinely during the life cycle of the activity or during the lifetime of the equipment | Almost Certain (>50% probability) | 5 | 5 (Moderate) | 10 (Substantial) | 15 (High) | 20 (Extreme) | 25 (Extreme)

## Risk Analysis (hidden)
Risk Level | Rating | Quantity
Low | 1 | 17
Moderate | 2 | 0
Significant | 3 | 0
High | 4 | 0
Extreme | 5 | 0
Total |  | 1
The formula and working cells are hidden. If you require access contact Darryl at Risk and Assurrance Service Centre RASC

## Data Sheet (hidden)
Control Effectiveness
Effective
Partially Effective
Not Effective
Other
Consequence Rating | Likelihood Rating | Hierarchy of Control
1 | 1 | Elimination
2 | 2 | Isolation
3 | 3 | Substitution
4 | 4 | Engineering
5 | 5 | Administration
Personal protective equipment (PPE)
Other