## Sheet1
|  | Start Date | End Date | Duration |  |  | Semester 1 | [14 empty] | Exams |  | Break |  |  |  |  | Semester 2
Task |  |  |  | Days | Weeks | week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Grab Rubik's cube | Total for Task | 2015-03-30 | 2015-05-03 | 35 | 5 | start | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02
| Research best vision system for detecting cube | 2015-03-30 | 2015-04-12 | 14 | 2 | end | 2015-03-01 | 2015-03-08 | 2015-03-15 | 2015-03-22 | 2015-03-29 | 2015-04-05 | 2015-04-12 | 2015-04-19 | 2015-04-26 | 2015-05-03 | 2015-05-10 | 2015-05-17 | 2015-05-24 | 2015-05-31 | 2015-06-07 | 2015-06-14 | 2015-06-21 | 2015-06-28 | 2015-07-05 | 2015-07-12 | 2015-07-19 | 2015-07-26 | 2015-08-02 | 2015-08-09 | 2015-08-16 | 2015-08-23 | 2015-08-30 | 2015-09-06 | 2015-09-13 | 2015-09-20 | 2015-09-27 | 2015-10-04 | 2015-10-11 | 2015-10-18 | 2015-10-25 | 2015-11-01 | 2015-11-08
| Motion planning to grab Rubik's cube | 2015-04-13 | 2015-04-26 | 14 | 2 |  | 2015-10-18: END
| Testing | 2015-04-27 | 2015-05-03 | 7 | 1
Identity Cube colours | Total for Task | 2015-05-04 | 2015-06-07 | 35 | 5
| Raise cube into head camera vision | 2015-05-04 | 2015-05-10 | 7 | 1
| Identify and save values of colours | 2015-05-11 | 2015-05-24 | 14 | 2
| Motion planning to allow all sides to be analysed | 2015-05-25 | 2015-05-31 | 7 | 1
| Testing | 2015-06-01 | 2015-06-07 | 7 | 1
Solve Rubik's cube | Total for Task | 2015-06-22 | 2015-07-26 | 35 | 5
| Research and determine best solution method | 2015-06-22 | 2015-07-12 | 21 | 3
| Implement into python and Testing | 2015-07-13 | 2015-07-26 | 14 | 2
Manipulate Rubik's cube | Total for Task | 2015-07-27 | 2015-08-30 | 35 | 5
| Motion planning for each face rotation required | 2015-07-27 | 2015-08-16 | 21 | 3
| Testing | 2015-08-17 | 2015-08-30 | 14 | 2
Return Rubik's cube | Total for Task | 2015-08-31 | 2015-09-13 | 14 | 2
| Place cube in original position and Testing | 2015-08-31 | 2015-09-13 | 14 | 2
Overall Algorithm | Total for Task | 2015-09-14 | 2015-10-11 | 28 | 4
| Testing and Finalising | 2015-09-14 | 2015-10-11 | 28 | 4
Semester 1 Assessments | Total for Task | 2015-04-27 | 2015-05-24 | 28 | 4
| Poster Presentation | 2015-04-27 | 2015-05-10 | 14 | 2
| Project Report | 2015-05-11 | 2015-05-24 | 14 | 2
|  |  |  | Total | 26
26 Weeks Avaliable
Formulas:
End Date = [Start Date]+(7*[Weeks])-1
End Date = [End Date, row below]
Start Date = [Start Date, row above]
Start Date = [End Date, row above]+1